## Summary
EHRP HOUSING RECONSTRUCTION PROGRESS
Summary Report
2024-04-20
Total Beneficiaries | 0
Total Enrollment | 0
First tranche received | 0
Constructions started | 99254
Second Tranche
Applications | 87014
Approved | 85073
Not approved | 1912
Second Tranche Received | 0
Third Tranche
Applications | 76656
Approved | 73906
Not approved | 2751
Third Tranche Received | 0
Constructions Completed | 73146
Source: CLPIU GMaLI / Building

## District_Details
EHRP HOUSING RECONSTRUCTION PROGRESS
2024-04-20
District | Total Beneficiaries | Enrolled Beneficiaries | First tranche received | Constructions started | Second tranche |  |  |  | Third tranche |  |  |  | Constructions completed
[5 empty] | Applications | Not approved | Approved | Payment | Applications | Not approved | Approved | Payment
Dhankuta | 3460 | 3186 | 3181 | 2986 | 2700 | 0 | 2700 | 2839 | 2090 | 0 | 2090 | 2534 | 1896
Sankhuwasabha | 2224 | 2067 | 2036 | 1500 | 1439 | 0 | 1439 | 1781 | 1329 | 0 | 1329 | 1736 | 968
Bhojpur | 6735 | 5848 | 5848 | 5185 | 4959 | 0 | 4959 | 5411 | 4528 | 0 | 4528 | 5217 | 3456
Solukhumbu | 12779 | 12444 | 12291 | 12842 | 11257 | 331 | 10897 | 11967 | 10272 | 357 | 9916 | 11848 | 11334
Khotang | 9977 | 9622 | 9622 | 10941 | 9853 | 1251 | 8602 | 9053 | 8602 | 1062 | 7540 | 8350 | 6056
Chitwan | 8443 | 8129 | 8129 | 8449 | 6863 | 0 | 6863 | 7678 | 6362 | 0 | 6362 | 7120 | 6401
Lamjung | 14887 | 14294 | 14048 | 13744 | 11242 | 11 | 11231 | 12013 | 9000 | 443 | 8557 | 9905 | 6899
Tanahun | 14856 | 14139 | 14139 | 13227 | 12321 | 0 | 12321 | 14139 | 11495 | 0 | 11495 | 11495 | 12367
Syangja | 9421 | 9070 | 9070 | 6419 | 5366 | 126 | 5240 | 6942 | 4275 | 116 | 4159 | 5927 | 5170
Kaski | 6602 | 6043 | 6044 | 5514 | 4922 | 174 | 4748 | 4688 | 4679 | 250 | 4429 | 4052 | 4322
Myagdi | 1065 | 954 | 954 | 777 | 777 | 0 | 777 | 954 | 758 | 7 | 751 | 755 | 713
Parbat | 5928 | 5665 | 5665 | 4716 | 4710 | 0 | 4710 | 4731 | 4185 | 22 | 4163 | 4011 | 4185
Baglung | 2553 | 2374 | 2374 | 2397 | 2038 | 0 | 2038 | 2025 | 2038 | 92 | 1946 | 1810 | 1965
Gulmi | 4723 | 4469 | 4209 | 4829 | 3522 | 16 | 3506 | 3557 | 2309 | 363 | 1946 | 3407 | 3309
Palpa | 5104 | 4576 | 4573 | 3725 | 3217 | 0 | 3217 | 3387 | 3005 | 22 | 2983 | 3075 | 2391
Nawalparasi | 1077 | 1071 | 1071 | 1092 | 1092 | 0 | 1092 | 1066 | 1082 | 0 | 1082 | 1058 | 1009
Arghakhanchi | 1225 | 1100 | 1100 | 911 | 736 | 3 | 733 | 830 | 647 | 17 | 630 | 772 | 705
Total | 0 | 0 | 0 | 99254 | 87014 | 1912 | 85073 | 0 | 76656 | 2751 | 73906 | 0 | 73146